## Aerial Status Report
Aerial Status Report
1/4/2025 5:33 PM
Job Name | Conversation | Project | Utility | Job Status | Assigned OSP | Last Edit | Field % | Trace % | No MR | Comm MR | Electric MR | PCO Required | Pole Count | Comments
FRM_5-1 | '1778525, 1778509, 1778478, 1778477, 1778474, 1778111 | FRM_5 | FEUS | Delivered | Hector | 2024-12-05 08:45 AM MST | 99.4% | 100.0% | 109 | 47 | 8 | 3 | 168 | Test 345
LP_CPF_Vallecito_S5 | '12345676 | LP_CPF | LPEA | Sent to PE | Anthony | 2024-12-30 03:11 AM MST | 100.0% | 100.0% | 72 | 0 | 0 | 0 | 72 | Test 123
GJD1-3_Extras | 'Riley to Populate |  | Xcel Energy | Approved for Construction | Riley | 2024-05-02 12:24 AM MST | 100.0% | 100.0% | 1 | 0 | 0 | 0 | 1
GJ_A5_1.1 | '1782232 | GJ_A5 | Xcel Energy | Pending Photo Annotation | Michael | 2025-01-03 07:32 AM MST | 95.6% | 82.9% | 25 | 11 | 0 | 0 | 45 | Test 0987