## Aerial Status Report
Aerial Status Report
1/1/2025 2:58 PM
Job Name | Utility | Job Status | OSP Engineer | Last Edit | Field % | Trace % | No MR | Comm MR | Electric MR | PCO Required | Pole Count
FRM_5-6 | FEUS | Approved for Construction | mitchell.melton@deeplydigital.com | 2024-11-05 04:03 AM MST | 98.2% | 93.6% | 12 | 36 | 5 | 2 | 56
FRM_AMAZON_FEED | FEUS | Approved for Construction | mitchell.melton@deeplydigital.com | 2024-11-06 01:06 AM MST | 0.0% | 100.0% | 3 | 10 | 0 | 0 | 13
FRM_3-3 | FEUS | Delivered | michael.espinal@deeplydigital.com | 2024-12-23 03:28 AM MST | 100.0% | 100.0% | 86 | 26 | 4 | 4 | 120 | Pending Field Collection | Pending Photo Annotation | Sent to PE | Pending EMR
FRM_3-4 | FEUS | Delivered | mitchell.melton@deeplydigital.com | 2024-12-10 04:33 AM MST | 97.8% | 100.0% | 73 | 14 | 4 | 0 | 91 | 50 | 74 | 6 | 1
FRM_3-5 | FEUS | Delivered | admin3@pothosgeospatial.com | 2024-11-13 01:11 AM MST | 100.0% | 100.0% | 101 | 11 | 0 | 0 | 112
FRM_3-6 | FEUS | Delivered | mitchell.melton@deeplydigital.com | 2024-12-16 02:48 AM MST | 97.2% | 100.0% | 100 | 2 | 3 | 1 | 106 | Approved for Construction | Hold | As Built | Delivered
FRM_5-1 | FEUS | Delivered | mitchell.melton@deeplydigital.com | 2024-12-05 08:45 AM MST | 99.4% | 100.0% | 109 | 47 | 8 | 3 | 168 | 25 | 43 | 1 | 105
FRM_5-3 | FEUS | Delivered | riley.mcneil@clearnetworx.com | 2024-12-03 03:06 AM MST | 100.0% | 100.0% | 113 | 64 | 6 | 0 | 183
FRM_3-2.2 | FEUS | Delivered | mitchell.melton@deeplydigital.com | 2024-10-30 06:58 AM MST | 98.4% | 100.0% | 110 | 13 | 1 | 1 | 125
FRM_3-7 S2 | FEUS | Delivered | mitchell.melton@deeplydigital.com | 2024-11-19 06:35 AM MST | 98.0% | 100.0% | 54 | 37 | 1 | 0 | 99
FRM_3-2.1_OCalc | FEUS | Delivered | mitchell.melton@deeplydigital.com | 2024-10-29 09:27 AM MST | 100.0% | 100.0% | 19 | 8 | 2 | 2 | 32
FRM_5-4_Zuni | FEUS | Delivered | mitchell.melton@deeplydigital.com | 2024-12-26 05:40 AM MST | 75.0% | 100.0% | 3 | 1 | 0 | 0 | 4
FRM_2-1_2-3 | FEUS | Hold | Unknown | Unknown | 34.0% | 0.0% | 0 | 0 | 0 | 0 | 50
FRM_2-2 | FEUS | Hold | Unknown | Unknown | 29.2% | 0.0% | 0 | 0 | 0 | 0 | 154
FRM_2-4 | FEUS | Hold | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 64
FRM_2-5_2-6 | FEUS | Hold | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 111
FRM_5-EXTRAS | FEUS | Junk | riley.mcneil@clearnetworx.com | 2024-10-31 03:16 AM MST | 100.0% | 14.3% | 12 | 3 | 0 | 0 | 26
FRM_3-EXTRAS | FEUS | Junk | mady@clearnetworx.com | 2024-08-21 10:33 AM MST | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 1
FRM_1-1 | FEUS | Pending Photo Annotation | Unknown | Unknown | 1.1% | 0.0% | 0 | 0 | 0 | 0 | 93
FRM_1-4.2 | FEUS | Pending Photo Annotation | Unknown | Unknown | 97.0% | 0.0% | 0 | 0 | 0 | 0 | 133
FRM_3-1 | FEUS | Pending Photo Annotation | michael.espinal@deeplydigital.com | 2024-12-06 02:29 AM MST | 100.0% | 100.0% | 77 | 7 | 0 | 1 | 85
FRM_1-5.1 | FEUS | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 180
FRM_1-5.2 | FEUS | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 130
FRM_4-1.4 | FEUS | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 108
FRM_5-2 | FEUS | Pending Photo Annotation | riley.mcneil@clearnetworx.com | 2024-12-03 06:19 AM MST | 100.0% | 100.0% | 147 | 16 | 1 | 0 | 164
FRM_4-1.1 | FEUS | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 157
FRM_4-1.2 | FEUS | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 170
FRM_4-1.3 | FEUS | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 97
FRM_5-4 | FEUS | Sent to PE | mitchell.melton@deeplydigital.com | 2024-12-06 06:13 AM MST | 96.6% | 98.7% | 87 | 1 | 0 | 0 | 88
FRM_3-7 S3 | FEUS | Sent to PE | michael.espinal@deeplydigital.com | 2024-12-26 04:46 AM MST | 100.0% | 100.0% | 85 | 7 | 2 | 4 | 99
FRM_3-6.2 | FEUS | Sent to PE | michael.espinal@deeplydigital.com | 2024-11-21 06:10 AM MST | 100.0% | 93.8% | 18 | 10 | 4 | 0 | 32
FRM_3-7 S1 | FEUS | Unknown | michael.espinal@deeplydigital.com | 2024-12-04 05:44 AM MST | 97.7% | 100.0% | 34 | 8 | 1 | 0 | 43
FRM_3Extras | FEUS | Unknown | riley.mcneil@clearnetworx.com | 2024-07-31 03:32 AM MST | 100.0% | 7.1% | 5 | 1 | 0 | 0 | 17
HWE-1G-EXT-K | HWE | Unknown | Unknown User | 2024-09-12 05:47 AM MST | 100.0% | 100.0% | 1 | 0 | 0 | 0 | 1
HWE-6A EXT G | HWE | Unknown | mitchell.melton@deeplydigital.com | 2024-10-08 02:52 AM MST | 100.0% | 100.0% | 2 | 0 | 0 | 0 | 2
HWE-6A EXT I | HWE | Unknown | mitchell.melton@deeplydigital.com | 2024-10-09 02:12 AM MST | 100.0% | 100.0% | 2 | 0 | 0 | 0 | 2
HWE-3D_EXT_A | HWE | Unknown | mitchell.melton@deeplydigital.com | 2024-10-04 06:45 AM MST | 100.0% | 100.0% | 2 | 0 | 0 | 0 | 2
HWE-7E_Ext_A.01 | HWE | Unknown | mitchell.melton@deeplydigital.com | 2024-11-06 08:01 AM MST | 100.0% | 98.6% | 4 | 0 | 0 | 0 | 4
HWE-6D_Ext_A.01 | HWE | Unknown | mitchell.melton@deeplydigital.com | 2024-11-26 07:19 AM MST | 100.0% | 8.9% | 1 | 0 | 0 | 0 | 3
HWE-6D_Ext_B.01 | HWE | Unknown | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 2
HWE-7E_Ext_A.01 Loading | HWE | Unknown | mitchell.melton@deeplydigital.com | 2024-11-06 08:01 AM MST | 100.0% | 98.6% | 4 | 0 | 0 | 0 | 4
HWE-7E_Ext_A.01 Copy - From Amplex Electric, Inc. | HWE | Unknown | mitchell.melton@deeplydigital.com | 2024-11-06 08:01 AM MST | 100.0% | 98.6% | 4 | 0 | 0 | 0 | 4
HWE-4A EXT A - From Amplex Electric, Inc. | HWE | Unknown | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 1
HWE_4C_EXT_C - From Amplex Electric, Inc. | HWE | Unknown | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 3
HWE-4C-EXT-D - From Amplex Electric, Inc. | HWE | Unknown | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 1
HWE-1G-EXT-L - From Amplex Electric, Inc. | HWE | Unknown | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 2
HWE-7A Ext i - From Amplex Electric, Inc. | HWE | Unknown | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 2
HWE-6A EXT D - From Amplex Electric, Inc. | HWE | Unknown | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 3
HWE-6A EXT G - From Amplex Electric, Inc. | HWE | Unknown | mitchell.melton@deeplydigital.com | 2024-10-08 02:52 AM MST | 100.0% | 100.0% | 2 | 0 | 0 | 0 | 2
HWE-2d Ext A - From Amplex Electric, Inc. | HWE | Unknown | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 10
HWE-6A EXT I - From Amplex Electric, Inc. | HWE | Unknown | mitchell.melton@deeplydigital.com | 2024-10-09 02:12 AM MST | 100.0% | 100.0% | 2 | 0 | 0 | 0 | 2
HWE-6A.mb-EXT-0A - From Amplex Electric, Inc. | HWE | Unknown | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 4
HWE-6A EXT J - From Amplex Electric, Inc. | HWE | Unknown | Unknown | Unknown | 100.0% | 0.7% | 0 | 0 | 0 | 0 | 10
HWE-6A.mb-EXT-B - From Amplex Electric, Inc. | HWE | Unknown | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 2
HWE-2D-EXT-B - From Amplex Electric, Inc. | HWE | Unknown | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 4
HWE-2D-EXT-C - From Amplex Electric, Inc. | HWE | Unknown | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 3
HWE-7E_Ext_A.01 - From Amplex Electric, Inc. | HWE | Unknown | mitchell.melton@deeplydigital.com | 2024-11-06 08:01 AM MST | 100.0% | 98.6% | 4 | 0 | 0 | 0 | 4
HWE-6D_Ext_A.01 - From Amplex Electric, Inc. | HWE | Unknown | mitchell.melton@deeplydigital.com | 2024-12-20 03:35 AM MST | 100.0% | 100.0% | 3 | 0 | 0 | 0 | 3
HWE-6D_Ext_B.01 - From Amplex Electric, Inc. | HWE | Unknown | mitchell.melton@deeplydigital.com | 2024-12-27 06:23 AM MST | 100.0% | 100.0% | 2 | 0 | 0 | 0 | 2
HWE-3C Ext E - From Amplex Electric, Inc. | HWE | Unknown | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 1
HWE-3C Ext F - From Amplex Electric, Inc. | HWE | Unknown | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 2
SPL_S1.1 | LPEA | Delivered | admin3@pothosgeospatial.com | 2024-06-21 06:03 AM MST | 100.0% | 98.6% | 46 | 0 | 17 | 12 | 77
SPL_S5.1 | LPEA | Delivered | admin3@pothosgeospatial.com | 2024-10-16 09:43 AM MST | 100.0% | 100.0% | 19 | 7 | 10 | 6 | 43
LP_CPF_Vallecito_S1 | LPEA | Delivered | admin3@pothosgeospatial.com | 2024-09-20 07:02 AM MST | 100.0% | 100.0% | 44 | 3 | 12 | 0 | 59
LP_CPF_Columbus_PineRiver | LPEA | Delivered | riley.mcneil@clearnetworx.com | 2024-08-29 12:52 AM MST | 100.0% | 100.0% | 66 | 4 | 10 | 2 | 82
LP_CPF_Vallecito_S4 | LPEA | Delivered | riley.mcneil@clearnetworx.com | 2024-12-17 09:59 AM MST | 98.9% | 100.0% | 88 | 5 | 1 | 0 | 94
SPL_EXTRAS | LPEA | Junk | jordan.demers@deeplydigital.com | 2024-07-25 09:22 AM MST | 34.3% | 11.9% | 22 | 6 | 5 | 3 | 166
LP_CPF_Vallecito_S2 | LPEA | Pending EMR | riley.mcneil@clearnetworx.com | 2024-09-13 12:50 AM MST | 100.0% | 100.0% | 69 | 5 | 11 | 1 | 87
Vallecito_S3_Extras | LPEA | Pending Field Collection | mady@clearnetworx.com | 2024-09-18 03:21 AM MST | 20.0% | 0.0% | 0 | 0 | 0 | 0 | 5
Vallecito_MidMile_Extras | LPEA | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 7
LP_CPF_Florida River | LPEA | Pending Photo Annotation | Unknown | Unknown | 96.8% | 0.0% | 0 | 0 | 0 | 0 | 158
LP_CPF_TweenLakes | LPEA | Pending Photo Annotation | zach.marin@deeplydigital.com | 2024-10-03 02:51 PM MST | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 72
LP_CPF_Mountain Shadow | LPEA | Pending Photo Annotation | Unknown | Unknown | 98.7% | 0.0% | 0 | 0 | 0 | 0 | 75
LP_CPF_LosRanchitos | LPEA | Pending Photo Annotation | Unknown | Unknown | 98.0% | 0.0% | 0 | 0 | 0 | 0 | 149
LP_CPF_FloridaNorth | LPEA | Pending Photo Annotation | Unknown | Unknown | 92.6% | 0.0% | 0 | 0 | 0 | 0 | 27
LP_CPF_Vallecito_S3 | LPEA | Pending Photo Annotation | mitchell.melton@deeplydigital.com | 2024-12-12 01:26 AM MST | 100.0% | 100.0% | 60 | 11 | 20 | 1 | 92
LP_CPF_Vallecito_S5 | LPEA | Pending Photo Annotation | admin3@pothosgeospatial.com | 2024-12-30 03:11 AM MST | 91.1% | 92.1% | 72 | 0 | 0 | 0 | 79
LP_CPF_Vallecito_S6 | LPEA | Pending Photo Annotation | riley.mcneil@clearnetworx.com | 2024-10-07 05:31 AM MST | 91.1% | 0.0% | 0 | 0 | 0 | 0 | 56
LP_CPF_Vallecito_S1.1 | LPEA | Pending Photo Annotation | mady@clearnetworx.com | 2024-09-07 07:58 AM MST | 100.0% | 5.4% | 0 | 2 | 0 | 0 | 48
Durango_W6 | LPEA | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 31
LP_CPF_Vallecito_MidMile | LPEA | Sent to PE | hector.aguilar@deeplydigital.com | 2024-12-31 05:38 AM MST | 99.6% | 78.3% | 204 | 3 | 0 | 0 | 258
SM_CPF_MASTER | SMPA | Pending Field Collection | jordan.demers@deeplydigital.com | 2024-12-18 09:44 AM MST | 34.9% | 16.9% | 23 | 8 | 0 | 9 | 175
Montrose Pole Trial | Unknown | Approved for Construction | admin3@pothosgeospatial.com | 2024-10-31 06:00 AM MST | 100.0% | 100.0% | 4 | 14 | 0 | 0 | 19
fruita extras | Unknown | Approved for Construction | michael.espinal@deeplydigital.com | 2024-08-26 06:41 AM MST | 100.0% | 88.6% | 34 | 14 | 0 | 0 | 48
GJCZ1-4 | Unknown | Approved for Construction | admin3@pothosgeospatial.com | 2024-05-24 02:26 AM MST | 100.0% | 98.0% | 119 | 48 | 50 | 1 | 218
GJ_D3-7 | Unknown | Approved for Construction | riley.mcneil@clearnetworx.com | 2024-09-30 07:58 AM MST | 96.0% | 100.0% | 5 | 10 | 8 | 0 | 25
Forest_Lakes_S1 | Unknown | Approved for Construction | riley.mcneil@clearnetworx.com | 2024-07-17 11:26 PM MST | 100.0% | 100.0% | 83 | 10 | 7 | 6 | 106
downtown durango_DU_E2 | Unknown | Approved for Construction | riley.mcneil@clearnetworx.com | 2024-07-25 06:55 AM MST | 100.0% | 98.9% | 13 | 54 | 16 | 4 | 87
DurangoW2_S1 | Unknown | Approved for Construction | admin3@pothosgeospatial.com | 2024-06-26 08:42 AM MST | 98.9% | 100.0% | 18 | 32 | 22 | 16 | 89
GJD1-3_Extras | Unknown | Approved for Construction | michael.espinal@deeplydigital.com | 2024-05-02 12:24 AM MST | 100.0% | 100.0% | 1 | 0 | 0 | 0 | 1
GJD1-2_Extras | Unknown | Approved for Construction | admin3@pothosgeospatial.com | 2024-05-13 05:45 AM MST | 100.0% | 100.0% | 4 | 22 | 1 | 2 | 29
downtown durango_DU_E3 | Unknown | Approved for Construction | riley.mcneil@clearnetworx.com | 2024-09-09 07:14 AM MST | 100.0% | 96.6% | 20 | 34 | 7 | 2 | 63
GJ_D1_9_Extras | Unknown | Approved for Construction | michael.espinal@deeplydigital.com | 2024-05-02 05:09 AM MST | 100.0% | 100.0% | 3 | 4 | 0 | 0 | 7
GJ_D1_7_Extras | Unknown | Approved for Construction | admin3@pothosgeospatial.com | 2024-05-22 02:49 AM MST | 100.0% | 100.0% | 0 | 1 | 0 | 0 | 1
GJ_A1_5_Extras | Unknown | Approved for Construction | michael.espinal@deeplydigital.com | 2024-05-02 02:42 AM MST | 100.0% | 100.0% | 5 | 0 | 0 | 0 | 5
GJ_A1_7_Extras | Unknown | Approved for Construction | admin3@pothosgeospatial.com | 2024-05-14 12:50 AM MST | 100.0% | 0.0% | 0 | 2 | 0 | 0 | 2
GJ_A3_1 | Unknown | Approved for Construction | admin3@pothosgeospatial.com | 2024-05-18 08:16 AM MST | 100.0% | 100.0% | 3 | 2 | 0 | 0 | 5
GJ_A3_8 | Unknown | Approved for Construction | admin3@pothosgeospatial.com | 2024-05-02 06:41 AM MST | 100.0% | 100.0% | 2 | 0 | 2 | 0 | 4
GJ_A3_CabinetFeeds | Unknown | Approved for Construction | michael.espinal@deeplydigital.com | 2024-05-03 04:57 AM MST | 100.0% | 100.0% | 17 | 9 | 0 | 2 | 28
GJ_A3_MiddleMiletoTemple | Unknown | Approved for Construction | admin3@pothosgeospatial.com | 2024-06-12 02:22 AM MST | 100.0% | 100.0% | 48 | 21 | 0 | 0 | 70
Naturita Recollect | Unknown | Approved for Construction | admin3@pothosgeospatial.com | 2024-09-17 02:21 AM MST | 100.0% | 100.0% | 9 | 1 | 0 | 0 | 10
Ouray_211Main | Unknown | Approved for Construction | riley.mcneil@clearnetworx.com | 2024-08-19 04:06 AM MST | 100.0% | 33.3% | 0 | 0 | 0 | 0 | 4
215 Silver Street Delta | Unknown | Approved for Construction | michael.espinal@deeplydigital.com | 2024-12-12 03:18 AM MST | 100.0% | 0.0% | 1 | 0 | 0 | 0 | 1
CORTEZS-1 | Unknown | As Built | michael.espinal@deeplydigital.com | 2024-05-15 05:13 AM MST | 22.8% | 93.7% | 0 | 0 | 1 | 0 | 114
Colona Town Design | Unknown | Delivered | Unknown | Unknown | 96.8% | 100.0% | 21 | 4 | 0 | 0 | 31
Gunnison City Wells 7 thru10 Pole Run | Unknown | Delivered | Unknown | Unknown | 100.0% | 100.0% | 8 | 1 | 0 | 0 | 9
CR 1 DORA | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-09-06 04:13 AM MST | 100.0% | 66.0% | 106 | 1 | 9 | 0 | 116
CR1 A DORA | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-05-30 03:36 PM MST | 100.0% | 97.4% | 82 | 1 | 1 | 0 | 84
CR-22 DORA | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-06-10 03:09 AM MST | 100.0% | 89.8% | 185 | 2 | 1 | 2 | 190
Montrose SC Trailer Park | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-07-16 04:31 AM MST | 100.0% | 100.0% | 6 | 0 | 4 | 0 | 10
Delta Hospital Run DMEA | Unknown | Delivered | Jonathon Cook | 2022-08-23 11:05 AM MST | 100.0% | 0.0% | 53 | 17 | 0 | 3 | 73
Bayfield Phase 1 | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-06-20 08:34 AM MST | 95.7% | 5.7% | 74 | 80 | 0 | 0 | 162
Delta Red House Tower and 1740 Tower DMEA | Unknown | Delivered | Unknown User | 2022-07-13 04:10 AM MST | 100.0% | 0.0% | 64 | 20 | 0 | 0 | 84
Ames CR 63L | Unknown | Delivered | Jonathon Cook | 2023-08-25 09:05 AM MST | 100.0% | 100.0% | 4 | 0 | 0 | 0 | 4
CortezN-3 | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-08-06 04:05 AM MST | 100.0% | 96.2% | 78 | 30 | 0 | 0 | 108
DurangoE3 | Unknown | Delivered | michael.espinal@deeplydigital.com | 2024-07-10 05:22 AM MST | 99.0% | 99.0% | 43 | 47 | 9 | 6 | 105
idlewild | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-05-13 08:00 AM MST | 99.0% | 0.0% | 91 | 6 | 0 | 0 | 98
GJCZ1-1 | Unknown | Delivered | zach.marin@deeplydigital.com | 2024-04-04 09:08 AM MST | 100.0% | 90.2% | 82 | 77 | 0 | 0 | 167
GJCZ1-2 | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-05-23 01:29 AM MST | 100.0% | 100.0% | 75 | 72 | 1 | 0 | 149
GJCZ1-3.S2 | Unknown | Delivered | michael.espinal@deeplydigital.com | 2024-07-25 01:28 PM MST | 99.0% | 100.0% | 49 | 52 | 0 | 4 | 105
GJCZ1-5 | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-06-26 06:56 AM MST | 100.0% | 99.5% | 102 | 80 | 0 | 1 | 186
GJCZ1-6 | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-05-30 03:23 AM MST | 100.0% | 95.8% | 62 | 31 | 38 | 0 | 131
electra lake | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-12-02 06:35 AM MST | 98.7% | 92.0% | 104 | 16 | 16 | 5 | 151
Mancos_S4 | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-12-22 05:04 PM MST | 100.0% | 100.0% | 29 | 24 | 19 | 0 | 72
CORTEZS-2 | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-05-16 06:11 AM MST | 100.0% | 94.1% | 52 | 18 | 0 | 0 | 70
CORTEZS-5 | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-12-16 02:16 AM MST | 100.0% | 98.7% | 66 | 30 | 0 | 0 | 96
CORTEZS-6 | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-09-17 04:23 AM MST | 100.0% | 91.9% | 49 | 36 | 9 | 0 | 95
GJOZ14-1 | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-06-04 07:16 AM MST | 100.0% | 94.6% | 25 | 20 | 19 | 1 | 66
GJOZ14-2 | Unknown | Delivered | brennan.reese@deeplydigital.com | 2024-06-06 04:57 AM MST | 100.0% | 100.0% | 53 | 43 | 4 | 1 | 101
GJOZ14-4 | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-06-27 01:43 AM MST | 99.2% | 95.3% | 77 | 22 | 23 | 0 | 122
GJOZ14-5 | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-11-14 03:24 AM MST | 100.0% | 100.0% | 55 | 68 | 0 | 4 | 127
GJOZ14-9 | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-06-19 01:48 PM MST | 100.0% | 100.0% | 63 | 12 | 18 | 1 | 94
GJOZ14-10 | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-06-05 10:52 AM MST | 100.0% | 100.0% | 39 | 6 | 14 | 0 | 60
HWY184Grant_MM_S3 | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-10-10 04:31 AM MST | 99.0% | 100.0% | 89 | 2 | 3 | 6 | 101
CortezN-5 | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2023-07-28 01:50 AM MST | 97.7% | 100.0% | 36 | 7 | 0 | 0 | 44
CortezN-6 | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-08-22 07:27 AM MST | 98.8% | 89.0% | 50 | 30 | 1 | 0 | 83
montrose-olathe | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-04-01 05:40 AM MST | 98.0% | 100.0% | 117 | 18 | 9 | 1 | 152
160extcortez | Unknown | Delivered | Jonathon Cook | 2024-01-06 08:57 AM MST | 100.0% | 100.0% | 11 | 0 | 0 | 0 | 11
Ridgway Charles St. | Unknown | Delivered | Jonathon Cook | 2023-12-08 08:41 AM MST | 100.0% | 100.0% | 2 | 2 | 0 | 0 | 4
62796 La Salle Rd | Unknown | Delivered | Jonathon Cook | 2023-12-27 08:36 AM MST | 100.0% | 0.0% | 2 | 1 | 0 | 0 | 3
montrose-black sheep | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-07-08 04:00 AM MST | 100.0% | 100.0% | 8 | 3 | 0 | 0 | 11
ignacio | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-01-30 01:18 AM MST | 100.0% | 100.0% | 2 | 0 | 0 | 0 | 2
CortezN-9 | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-09-27 12:04 PM MST | 100.0% | 100.0% | 60 | 16 | 7 | 2 | 85
lincolnrd Montrose | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-07-03 01:41 AM MST | 100.0% | 100.0% | 20 | 0 | 1 | 0 | 21
Montrose Woods Crossing Feedv2 | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-03-05 09:48 AM MST | 100.0% | 100.0% | 20 | 6 | 0 | 0 | 27
DurangoW6_S1 | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-11-27 04:15 AM MST | 100.0% | 100.0% | 37 | 61 | 1 | 13 | 114
DurangoW7_S1 | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-10-03 08:45 AM MST | 98.0% | 100.0% | 18 | 20 | 9 | 2 | 50
Delta F Road and Hospital Run Extras | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-06-20 10:48 AM MST | 100.0% | 100.0% | 1 | 0 | 0 | 1 | 2
GJ_A3_3 | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-06-05 07:33 AM MST | 100.0% | 83.3% | 7 | 0 | 0 | 0 | 7
downtown durango_DU_E4 | Unknown | Delivered | jordan.demers@deeplydigital.com | 2024-08-15 11:39 AM MST | 96.4% | 98.0% | 30 | 21 | 4 | 0 | 55
GJCZ1-3_S1 | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-05-10 05:30 AM MST | 100.0% | 94.7% | 11 | 25 | 2 | 0 | 38
GJCZ1-1_New_Model | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-05-23 02:45 AM MST | 100.0% | 88.7% | 84 | 79 | 0 | 0 | 163
Delta North DMEA Fix | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-05-31 05:34 AM MST | 96.2% | 100.0% | 3 | 12 | 9 | 2 | 26
SPL_S2.1 | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-10-21 03:17 AM MST | 100.0% | 100.0% | 67 | 1 | 17 | 23 | 108
SPL_S3.1 | Unknown | Delivered | jordan.demers@deeplydigital.com | 2024-06-21 05:22 AM MST | 100.0% | 100.0% | 74 | 5 | 18 | 19 | 116
SPL_S4.1 | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-08-03 01:08 AM MST | 100.0% | 99.0% | 76 | 2 | 16 | 13 | 107
SPL_S6.1 | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-12-10 04:19 AM MST | 98.9% | 97.7% | 65 | 2 | 16 | 10 | 93
Ouray_550TimberXing | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-11-06 09:43 AM MST | 100.0% | 100.0% | 0 | 2 | 0 | 0 | 2
DurangoW1_S1 | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-06-20 01:25 AM MST | 95.1% | 100.0% | 21 | 17 | 0 | 2 | 41
Forest_Lakes_S3 | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-08-12 09:02 AM MST | 100.0% | 100.0% | 67 | 2 | 14 | 10 | 93
Forest_Lakes_S2 | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-07-22 11:51 PM MST | 100.0% | 100.0% | 49 | 3 | 15 | 3 | 70
Middle Mile A and C Part 1 | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-07-02 01:21 AM MST | 100.0% | 100.0% | 96 | 27 | 30 | 0 | 154
FRM_5-5 | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-11-13 11:56 PM MST | 99.4% | 100.0% | 92 | 51 | 13 | 0 | 156
SkyView_Durango | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-08-24 03:26 AM MST | 100.0% | 100.0% | 6 | 6 | 2 | 0 | 14
downtown durango_DU_E3_Rework | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-03-30 02:20 AM MST | 100.0% | 100.0% | 0 | 2 | 1 | 0 | 3
HWY160Grant_MM_S2 | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-08-14 02:38 AM MST | 100.0% | 100.0% | 95 | 0 | 2 | 0 | 97
Feed to Rose Creek Subdivision Fruita, K Road | Unknown | Delivered | michael.espinal@deeplydigital.com | 2024-08-16 05:33 AM MST | 0.0% | 100.0% | 0 | 0 | 0 | 0 | 12
Fruit Park Road Extension Montrose | Unknown | Delivered | michael.espinal@deeplydigital.com | 2024-07-22 03:55 AM MST | 100.0% | 100.0% | 7 | 0 | 0 | 0 | 7
712 1565 Rd Delta | Unknown | Delivered | michael.espinal@deeplydigital.com | 2024-08-13 06:53 AM MST | 100.0% | 0.0% | 4 | 0 | 0 | 0 | 4
Forest_Lakes_Extras | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-07-31 12:42 AM MST | 100.0% | 100.0% | 5 | 1 | 2 | 1 | 9
HWY184Grant_MM_S1 | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-08-23 09:08 AM MST | 99.0% | 100.0% | 86 | 7 | 2 | 5 | 100
HWY184Grant_MM_S2 | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-08-26 07:33 AM MST | 100.0% | 100.0% | 97 | 0 | 4 | 3 | 104
GJ_D3-6 | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-10-01 03:20 AM MST | 100.0% | 100.0% | 16 | 11 | 3 | 0 | 30
Montrose Infill North_S1 | Unknown | Delivered | mitchell.melton@deeplydigital.com | 2024-09-24 02:20 AM MST | 99.0% | 100.0% | 94 | 0 | 0 | 2 | 96
Montrose Infill North_S2 | Unknown | Delivered | admin3@pothosgeospatial.com | 2024-10-10 11:02 AM MST | 97.8% | 100.0% | 132 | 2 | 2 | 0 | 136
GJ_D2-1MM | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-08-28 12:59 AM MST | 100.0% | 100.0% | 7 | 4 | 2 | 0 | 13
CortezN-9App2 | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-10-09 12:02 AM MST | 100.0% | 100.0% | 48 | 4 | 4 | 0 | 56
GJ_D4_Extras | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-12-09 06:30 AM MST | 100.0% | 100.0% | 1 | 3 | 1 | 0 | 6
GJ_A3-3.1 | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-11-08 02:55 AM MST | 100.0% | 100.0% | 5 | 2 | 0 | 0 | 7
Cortez_Extras | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-12-26 04:51 AM MST | 100.0% | 100.0% | 11 | 2 | 3 | 0 | 16
Mancos_S1 | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-12-16 03:32 PM MST | 100.0% | 100.0% | 16 | 12 | 19 | 0 | 47
Mancos_CDOT | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-12-18 10:16 PM MST | 100.0% | 100.0% | 25 | 23 | 10 | 1 | 59
Mancos_S2 | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-12-18 01:08 AM MST | 97.2% | 100.0% | 33 | 29 | 10 | 0 | 72
Mancos_S3 | Unknown | Delivered | riley.mcneil@clearnetworx.com | 2024-12-11 01:04 AM MST | 100.0% | 100.0% | 45 | 4 | 10 | 1 | 60
Ohpir to Silverton | Unknown | Hold | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 133
Pleasant Valley | Unknown | Hold | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 108
Olathe Redundant Path - Jig Rd | Unknown | Hold | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 303
Montrose SCC Mainline Upgrade | Unknown | Hold | Jonathon Cook | 2023-01-25 02:13 AM MST | 100.0% | 0.5% | 136 | 67 | 0 | 0 | 203
Montrose SCC Mainline Overhaul Extras | Unknown | Hold | Unknown User | 2022-07-26 01:44 AM MST | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 47
Delta Highway 348 | Unknown | Hold | Jonathon Cook | 2023-06-06 08:39 AM MST | 99.6% | 0.0% | 218 | 9 | 0 | 0 | 230
Norwood Z42 Rd | Unknown | Hold | riley.mcneil@clearnetworx.com | 2023-03-14 07:51 AM MST | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 22
Montrose Woods Crossing Extras | Unknown | Hold | Jonathon Cook | 2023-02-05 10:24 AM MST | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 30
DMEA Rural Montrose | Unknown | Hold | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 322
CortezN-8 | Unknown | Hold | zach.marin@deeplydigital.com | 2024-01-31 01:55 AM MST | 100.0% | 96.9% | 60 | 5 | 0 | 0 | 65
MACK | Unknown | Hold | Unknown | Unknown | 97.9% | 0.0% | 0 | 0 | 0 | 0 | 711
CORTEZS-4 | Unknown | Hold | admin3@pothosgeospatial.com | 2024-05-15 09:25 AM MST | 100.0% | 97.2% | 76 | 34 | 2 | 0 | 112
GJOZ14-6 | Unknown | Hold | michael.espinal@deeplydigital.com | 2024-05-31 07:19 AM MST | 98.2% | 92.2% | 40 | 55 | 2 | 6 | 112
GJOZ14-8 | Unknown | Hold | gavin.walsh@deeplydigital.com | 2023-07-18 07:15 AM MST | 98.9% | 0.0% | 1 | 0 | 0 | 0 | 88
CortezN-7 | Unknown | Hold | zach.marin@deeplydigital.com | 2024-01-30 02:44 AM MST | 100.0% | 97.1% | 135 | 2 | 0 | 0 | 137
GJ_D2-2 | Unknown | Hold | riley.mcneil@clearnetworx.com | 2024-08-05 05:22 AM MST | 90.3% | 26.5% | 6 | 9 | 5 | 0 | 72
GJ_D2-3 | Unknown | Hold | admin3@pothosgeospatial.com | 2024-07-30 04:01 AM MST | 100.0% | 43.9% | 11 | 8 | 4 | 6 | 68
GJ_D2-6-7 | Unknown | Hold | colin.krebs@deeplydigital.com | 2024-08-02 04:23 AM MST | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 36
DowntownDurango3 | Unknown | Hold | riley.mcneil@clearnetworx.com | 2023-05-05 04:55 AM MST | 100.0% | 52.9% | 5 | 3 | 0 | 0 | 88
montrose-olathe extras | Unknown | Hold | riley.mcneil@clearnetworx.com | 2023-11-18 11:31 AM MST | 100.0% | 95.7% | 71 | 24 | 0 | 0 | 97
FRM2-2 | Unknown | Hold | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 80
doraextras | Unknown | Hold | zach.marin@deeplydigital.com | 2024-06-06 04:35 AM MST | 33.3% | 0.0% | 3 | 0 | 0 | 0 | 138
GJOZ14.Extras | Unknown | Hold | jordan.demers@deeplydigital.com | 2024-08-06 02:22 AM MST | 97.6% | 10.5% | 14 | 5 | 1 | 1 | 41
GJOZ14_1_Phase2 | Unknown | Hold | riley.mcneil@clearnetworx.com | 2024-05-23 08:13 AM MST | 96.4% | 70.8% | 18 | 1 | 6 | 0 | 28
GJOZ14-9_Phase2 | Unknown | Hold | brennan.reese@deeplydigital.com | 2024-06-06 04:29 AM MST | 100.0% | 64.6% | 46 | 12 | 12 | 0 | 95
GJOZ14-10_phase2 | Unknown | Hold | gavin.walsh@deeplydigital.com | 2023-07-18 07:12 AM MST | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 26
downtowndurango_feed | Unknown | Hold | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 9
Middle Mile A | Unknown | Hold | riley.mcneil@clearnetworx.com | 2024-06-17 01:19 AM MST | 96.5% | 38.0% | 30 | 5 | 9 | 0 | 113
Opossum Lane Extension Montrose | Unknown | Hold | michael.espinal@deeplydigital.com | 2024-07-22 05:38 AM MST | 100.0% | 33.3% | 1 | 1 | 0 | 0 | 4
GJ_A4_7-3_Xcel | Unknown | Hold | Unknown | Unknown | 97.2% | 0.0% | 0 | 0 | 0 | 0 | 71
GJ_A4_1 | Unknown | Hold | zach.marin@deeplydigital.com | 2024-12-09 10:30 AM MST | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 59
GJ_A4_3 | Unknown | Hold | ethan.walker@deeplydigital.com | 2024-11-01 05:43 AM MST | 96.2% | 0.0% | 0 | 0 | 0 | 0 | 133
GJ_A4_5 | Unknown | Hold | zach.marin@deeplydigital.com | 2024-10-07 09:47 AM MST | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 78
GJ_A4_7 | Unknown | Hold | Unknown | Unknown | 93.8% | 0.0% | 0 | 0 | 0 | 0 | 32
GJ_A4_8 | Unknown | Hold | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 74
GJ_A4_9 | Unknown | Hold | Unknown | Unknown | 75.0% | 0.0% | 0 | 0 | 0 | 0 | 8
GJ_A4_10 | Unknown | Hold | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 30
GVH Annex | Unknown | Junk | Unknown | Unknown | 100.0% | 0.0% | 10 | 0 | 0 | 0 | 10
Montrose Jimmers Pole Run | Unknown | Junk | Unknown | Unknown | 100.0% | 0.0% | 70 | 0 | 0 | 0 | 70
SMPA Sub to 2 Rivers | Unknown | Junk | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 18
Delta Doughty Steel | Unknown | Junk | Unknown | Unknown | 100.0% | 0.0% | 5 | 0 | 0 | 0 | 5
Norwood SMPA Pole Report 2020 | Unknown | Junk | Unknown | Unknown | 100.0% | 0.0% | 64 | 22 | 0 | 0 | 88
Ouray SMPA Pole Report 2020 | Unknown | Junk | Unknown | Unknown | 100.0% | 0.0% | 45 | 9 | 0 | 0 | 54
Redvale SMPA Pole Report 2020 | Unknown | Junk | Unknown | Unknown | 100.0% | 0.0% | 37 | 15 | 0 | 0 | 52
Montrose Jimmers Pole Run Phase 1 | Unknown | Junk | Unknown | Unknown | 100.0% | 0.0% | 29 | 0 | 0 | 0 | 29
Montrose Jimmers Pole Phase 2 | Unknown | Junk | Unknown | Unknown | 100.0% | 0.0% | 31 | 0 | 0 | 0 | 31
Ridgway SMPA Pole Report 2020 | Unknown | Junk | Unknown | Unknown | 100.0% | 0.0% | 66 | 10 | 0 | 0 | 76
Elk Meadows | Unknown | Junk | admin3@pothosgeospatial.com | 2024-05-28 08:17 AM MST | 29.0% | 23.3% | 9 | 0 | 0 | 0 | 31
Whispering/Sunshine DORA | Unknown | Junk | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 26
Dexter Creek DORA | Unknown | Junk | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 20
Delta Garnet Mesa | Unknown | Junk | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 160
Montrose CNL | Unknown | Junk | Unknown | Unknown | 90.0% | 0.0% | 0 | 0 | 0 | 0 | 20
Naturita Extras | Unknown | Junk | Jonathon Cook | 2022-10-06 08:42 AM MST | 100.0% | 0.0% | 2 | 0 | 0 | 0 | 2
CortezN-1 | Unknown | Junk | admin3@pothosgeospatial.com | 2024-07-31 07:38 AM MST | 99.6% | 96.2% | 195 | 68 | 1 | 0 | 264
CortezN-2 | Unknown | Junk | admin3@pothosgeospatial.com | 2024-08-01 05:02 AM MST | 100.0% | 93.7% | 64 | 53 | 0 | 0 | 117
CortezN-4 | Unknown | Junk | admin3@pothosgeospatial.com | 2024-08-01 04:58 AM MST | 98.9% | 90.9% | 55 | 27 | 5 | 1 | 91
GJCZ3 | Unknown | Junk | gavin.walsh@deeplydigital.com | 2023-08-09 08:46 AM MST | 85.5% | 0.0% | 0 | 0 | 0 | 0 | 550
WHITEWATER | Unknown | Junk | gavin.walsh@deeplydigital.com | 2023-10-25 04:05 PM MST | 82.9% | 0.0% | 0 | 0 | 0 | 0 | 321
Ogden Montrose | Unknown | Junk | mitchell.melton@deeplydigital.com | 2024-09-19 12:56 AM MST | 100.0% | 100.0% | 32 | 2 | 1 | 11 | 46
CORTEZS-1_DD | Unknown | Junk | admin3@pothosgeospatial.com | 2024-05-16 05:29 AM MST | 100.0% | 94.0% | 53 | 34 | 1 | 0 | 88
CORTEZS-2_DD | Unknown | Junk | admin3@pothosgeospatial.com | 2024-05-16 06:11 AM MST | 100.0% | 94.1% | 52 | 18 | 0 | 0 | 70
CORTEZS-3_DD | Unknown | Junk | admin3@pothosgeospatial.com | 2024-07-31 07:12 AM MST | 100.0% | 96.0% | 60 | 36 | 8 | 0 | 104
downtowndurango2_Extras | Unknown | Junk | Unknown | Unknown | 100.0% | 0.0% | 1 | 0 | 2 | 1 | 5
GJCZ1-5_Phase2 | Unknown | Junk | michael.espinal@deeplydigital.com | 2024-04-26 05:51 AM MST | 100.0% | 100.0% | 7 | 6 | 0 | 0 | 13
SPL_Transmission | Unknown | Junk | jordan.demers@deeplydigital.com | 2024-07-16 10:58 AM MST | 100.0% | 100.0% | 13 | 0 | 0 | 0 | 35
Forest_Lakes_Master | Unknown | Junk | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 339
GJ_CZ1-3extras | Unknown | Junk | colin.krebs@deeplydigital.com | 2024-05-15 02:22 AM MST | 100.0% | 100.0% | 19 | 11 | 1 | 1 | 38
ElectraLake_Extras | Unknown | Junk | riley.mcneil@clearnetworx.com | 2024-12-26 06:56 AM MST | 100.0% | 100.0% | 6 | 0 | 0 | 0 | 6
Montrose Infill South | Unknown | Junk | michael.espinal@deeplydigital.com | 2024-09-03 06:15 AM MST | 98.1% | 0.0% | 6 | 0 | 0 | 0 | 261
CortezExtras | Unknown | Junk | admin3@pothosgeospatial.com | 2024-12-16 02:24 AM MST | 100.0% | 91.0% | 27 | 7 | 8 | 0 | 91
Durango_W_extras | Unknown | Junk | riley.mcneil@clearnetworx.com | 2023-05-29 03:45 AM MST | 92.5% | 0.0% | 0 | 0 | 0 | 0 | 67
GJ_D1-3_Extras | Unknown | Junk | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 3
GJ_D3-6_Extras | Unknown | Junk | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 8
Maple Grove Fiber Overbuild | Unknown | Pending Field Collection | Unknown User | 2022-06-15 07:27 AM MST | 62.5% | 0.0% | 5 | 0 | 0 | 0 | 8
Cedaredge | Unknown | Pending Field Collection | Unknown | Unknown | 20.1% | 0.0% | 0 | 0 | 0 | 0 | 483
Paonia | Unknown | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 382
Hotchkiss | Unknown | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 227
GJ_D7 | Unknown | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 131
GJ_D8_1_Xcel | Unknown | Pending Field Collection | Unknown | Unknown | 82.4% | 0.0% | 0 | 0 | 0 | 0 | 17
GJ_D8_1_GVP | Unknown | Pending Field Collection | Unknown | Unknown | 60.0% | 0.0% | 0 | 0 | 0 | 0 | 10
GJ_D8_3 | Unknown | Pending Field Collection | Unknown | Unknown | 62.8% | 0.0% | 0 | 0 | 0 | 0 | 78
GJ_D8_5 | Unknown | Pending Field Collection | Unknown | Unknown | 91.1% | 0.0% | 0 | 0 | 0 | 0 | 45
HWY_160.7 | Unknown | Pending Field Collection | Unknown | Unknown | 55.9% | 0.0% | 0 | 0 | 0 | 0 | 68
HWY_184.16 | Unknown | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 58
GJ_D9-3 | Unknown | Pending Field Collection | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 10
GJ_D9-4 | Unknown | Pending Field Collection | Unknown | Unknown | 47.8% | 0.0% | 0 | 0 | 0 | 0 | 69
GJ_D9-5 | Unknown | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 104
GJ_D9-6 | Unknown | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 147
GJ_D9-7 | Unknown | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 59
Montrose_MarineRd. | Unknown | Pending Field Collection | Unknown | Unknown | 80.3% | 0.0% | 0 | 0 | 0 | 0 | 61
FRM_4-5 | Unknown | Pending Field Collection | Unknown | Unknown | 83.0% | 0.0% | 0 | 0 | 0 | 0 | 165
Battlement_Mesa | Unknown | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 37
GJ_D1_extras | Unknown | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 2
CR_220Durango | Unknown | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 4
HWY_184.1 | Unknown | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 52
HWY_184.2 | Unknown | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 55
HWY_184.3 | Unknown | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 56
HWY_184.4 | Unknown | Pending Field Collection | Unknown | Unknown | 18.0% | 0.0% | 0 | 0 | 0 | 0 | 50
HWY_184.5 | Unknown | Pending Field Collection | Unknown | Unknown | 98.4% | 0.0% | 0 | 0 | 0 | 0 | 62
HWY_184.6 | Unknown | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 55
HWY_184.7 | Unknown | Pending Field Collection | Unknown | Unknown | 24.3% | 0.0% | 0 | 0 | 0 | 0 | 37
HWY_184.8 | Unknown | Pending Field Collection | Unknown | Unknown | 63.6% | 0.0% | 0 | 0 | 0 | 0 | 44
HWY_184.9 | Unknown | Pending Field Collection | Unknown | Unknown | 36.1% | 0.0% | 0 | 0 | 0 | 0 | 61
HWY_184.10 | Unknown | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 51
HWY_184.11 | Unknown | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 61
HWY_184.12 | Unknown | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 63
HWY_184.13 | Unknown | Pending Field Collection | Unknown | Unknown | 77.2% | 0.0% | 0 | 0 | 0 | 0 | 57
HWY_184.14 | Unknown | Pending Field Collection | Unknown | Unknown | 72.9% | 0.0% | 0 | 0 | 0 | 0 | 59
HWY_184.15 | Unknown | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 58
HWY_160.1 | Unknown | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 60
HWY_160.2 | Unknown | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 44
HWY_160.3 | Unknown | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 49
HWY_160.4 | Unknown | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 53
HWY_160.5 | Unknown | Pending Field Collection | Unknown | Unknown | 60.4% | 0.0% | 0 | 0 | 0 | 0 | 48
HWY_160.6 | Unknown | Pending Field Collection | Unknown | Unknown | 7.3% | 0.0% | 0 | 0 | 0 | 0 | 55
VZN_Parachute | Unknown | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 3
Spring Creek Rebuild | Unknown | Pending Photo Annotation | zach.marin@deeplydigital.com | 2023-12-11 07:02 AM MST | 100.0% | 0.0% | 84 | 49 | 0 | 0 | 133
Bayfield | Unknown | Pending Photo Annotation | Jonathon Cook | 2023-02-09 10:09 AM MST | 97.6% | 0.0% | 98 | 15 | 0 | 0 | 248
Silverton | Unknown | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 14 | 15 | 1 | 0 | 239
Orvis Hot Springs Fiber Drop SMPA | Unknown | Pending Photo Annotation | Unknown User | 2022-06-09 03:33 AM MST | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 22
DurangoE1 | Unknown | Pending Photo Annotation | michael.espinal@deeplydigital.com | 2024-06-03 06:27 AM MST | 100.0% | 20.3% | 6 | 7 | 1 | 2 | 79
downtowndurango2 | Unknown | Pending Photo Annotation | admin3@pothosgeospatial.com | 2024-10-18 09:00 AM MST | 100.0% | 91.0% | 18 | 34 | 11 | 11 | 86
dolores | Unknown | Pending Photo Annotation | riley.mcneil@clearnetworx.com | 2024-03-21 05:19 PM MST | 99.6% | 7.0% | 22 | 8 | 0 | 0 | 237
cortezmisc | Unknown | Pending Photo Annotation | anthony.santana@deeplydigital.com | 2024-12-31 06:17 AM MST | 100.0% | 47.6% | 38 | 0 | 0 | 0 | 67
GJOZ14-7 | Unknown | Pending Photo Annotation | gavin.walsh@deeplydigital.com | 2023-07-24 02:38 AM MST | 98.9% | 0.0% | 0 | 0 | 0 | 0 | 89
olathe | Unknown | Pending Photo Annotation | zach.marin@deeplydigital.com | 2023-12-05 03:56 AM MST | 100.0% | 75.6% | 49 | 23 | 0 | 0 | 93
GJ_D2-1 | Unknown | Pending Photo Annotation | gavin.walsh@deeplydigital.com | 2024-08-01 07:11 AM MST | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 106
DowntownDurango3_S1 | Unknown | Pending Photo Annotation | admin3@pothosgeospatial.com | 2024-06-03 03:52 AM MST | 95.9% | 95.8% | 4 | 39 | 2 | 2 | 49
Fruita Palisade Middle Mile - I-70 and 24 Rd to Patterson and 29 Rd | Unknown | Pending Photo Annotation | riley.mcneil@clearnetworx.com | 2024-03-11 04:41 AM MST | 95.6% | 0.9% | 1 | 1 | 0 | 0 | 113
G rd. 25 crossing | Unknown | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 4
timbe ridge csg. | Unknown | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 9
FRM_1-2 | Unknown | Pending Photo Annotation | Unknown | Unknown | 0.8% | 0.0% | 0 | 0 | 0 | 0 | 131
FRM_1-3 | Unknown | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 54
Montrose Infill South_S2 | Unknown | Pending Photo Annotation | michael.espinal@deeplydigital.com | 2024-10-14 04:31 AM MST | 99.3% | 100.0% | 123 | 9 | 1 | 0 | 137
PineRiver_Feed | Unknown | Pending Photo Annotation | riley.mcneil@clearnetworx.com | 2024-12-04 09:55 AM MST | 100.0% | 100.0% | 13 | 0 | 0 | 1 | 14
GJ_A5_1.1 | Unknown | Pending Photo Annotation | michael.espinal@deeplydigital.com | 2024-12-31 07:51 AM MST | 96.4% | 15.4% | 5 | 2 | 0 | 0 | 55
GJ_A5_2 | Unknown | Pending Photo Annotation | Unknown | Unknown | 72.5% | 0.0% | 0 | 0 | 0 | 0 | 40
GJ_A5_3 | Unknown | Pending Photo Annotation | gavin.walsh@deeplydigital.com | 2023-08-08 08:17 AM MST | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 55
GJ_A5_4 | Unknown | Pending Photo Annotation | gavin.walsh@deeplydigital.com | 2023-08-03 09:01 AM MST | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 61
GJ_A5_5 | Unknown | Pending Photo Annotation | riley.mcneil@clearnetworx.com | 2024-10-03 09:29 AM MST | 61.4% | 12.1% | 2 | 1 | 1 | 1 | 57
Durango_BODO-B-1 | Unknown | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 72
Durango_W8 | Unknown | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 67
Durango_W7 | Unknown | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 49
Durango_N5 | Unknown | Pending Photo Annotation | riley.mcneil@clearnetworx.com | 2023-06-07 09:49 AM MST | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 46
Durango_TS1 | Unknown | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 33
Durango_W2 | Unknown | Pending Photo Annotation | Unknown | Unknown | 97.8% | 0.0% | 0 | 0 | 0 | 0 | 46
Durango_W3 | Unknown | Pending Photo Annotation | riley.mcneil@clearnetworx.com | 2023-05-25 01:38 PM MST | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 60
Durango_W4 | Unknown | Pending Photo Annotation | riley.mcneil@clearnetworx.com | 2023-05-25 01:34 PM MST | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 48
Durango_W5 | Unknown | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 51
FRM_4-4.1 | Unknown | Pending Photo Annotation | Unknown | Unknown | 98.7% | 0.0% | 0 | 0 | 0 | 0 | 77
FRM_4-4.2 | Unknown | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 105
FRM_4-4.3 | Unknown | Pending Photo Annotation | Unknown | Unknown | 98.8% | 0.0% | 0 | 0 | 0 | 0 | 82
GJ_D8_2 | Unknown | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 18
GJ_D8_4 | Unknown | Pending Photo Annotation | Unknown | Unknown | 93.6% | 0.0% | 0 | 0 | 0 | 0 | 172
Sunray_Casino | Unknown | Pending Photo Annotation | riley.mcneil@clearnetworx.com | 2024-11-21 07:14 AM MST | 92.6% | 20.8% | 9 | 2 | 0 | 0 | 54
GJ_D9-2 | Unknown | Pending Photo Annotation | Unknown | Unknown | 78.2% | 0.0% | 0 | 0 | 0 | 0 | 55
FRM_4-2.3 | Unknown | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 96
FRM_4-3.4 | Unknown | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 114
FRM_4-2.1 | Unknown | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 125
FRM_4-2.2 | Unknown | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 159
FRM_4-3.1 | Unknown | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 142
FRM_4-3.2 | Unknown | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 149
FRM_4-3.3 | Unknown | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 98
FRM_1-4.1 | Unknown | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 130
Mancos_CDOT_Rejects | Unknown | Pending Photo Annotation | riley.mcneil@clearnetworx.com | 2024-12-03 08:14 AM MST | 100.0% | 100.0% | 1 | 4 | 1 | 0 | 6
Fruita_J-rd_Extension_GVP | Unknown | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 35
Electra_TowerFeed | Unknown | Pending Photo Annotation | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 4
Gj_A5_1.2 | Unknown | Pending Photo Annotation | Unknown | Unknown | 90.3% | 0.0% | 0 | 0 | 0 | 0 | 31
cr5 ridgway | Unknown | Sent to PE | admin3@pothosgeospatial.com | 2024-05-20 05:23 AM MST | 100.0% | 0.0% | 16 | 0 | 0 | 0 | 16
Montrose Infill South_S1 | Unknown | Sent to PE | michael.espinal@deeplydigital.com | 2024-10-18 03:01 AM MST | 100.0% | 100.0% | 112 | 11 | 1 | 4 | 128
Redvale SMPA Poles | Unknown | Unknown | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 397
Mountain Annies Colona Connect | Unknown | Unknown | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 32
TBN Ranch Build with Aerial | Unknown | Unknown | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 240
SMPA Connect to Vista Terrace | Unknown | Unknown | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 23
Norwood CDOT | Unknown | Unknown | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 41
Gunnison to CB All Aerial to Sub | Unknown | Unknown | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 546
Gunnison to CB Initial Design with Aerial | Unknown | Unknown | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 417
Norwood Z42 Pole Run | Unknown | Unknown | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 17
Uncompahgre DORA | Unknown | Unknown | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 105
Riverside/DMEA Uncompahgre DORA | Unknown | Unknown | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 237
Pahgre/Kinikin DORA | Unknown | Unknown | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 304
Ouray Ice Park Connection | Unknown | Unknown | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 6
HWY 145 Grant - Naturita and Naturita Feed | Unknown | Unknown | zach.marin@deeplydigital.com | 2024-04-03 09:51 AM MST | 98.3% | 0.3% | 259 | 32 | 0 | 0 | 302
Nucla Connection | Unknown | Unknown | admin3@pothosgeospatial.com | 2024-04-29 04:42 AM MST | 99.5% | 2.0% | 473 | 70 | 0 | 0 | 551
Hwy145- Redvale/Norwood | Unknown | Unknown | Jonathon Cook | 2022-09-07 11:20 AM MST | 100.0% | 1.2% | 155 | 18 | 0 | 0 | 174
Montrose SCC - Kelly | Unknown | Unknown | riley.mcneil@clearnetworx.com | 2023-02-10 07:27 AM MST | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 28
Delta County SD Warehouse | Unknown | Unknown | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 39
Delta North DMEA | Unknown | Unknown | Unknown User | 2024-02-14 06:37 AM MST | 99.8% | 0.0% | 359 | 68 | 0 | 1 | 428
Delta Garnet Mesa DMEA | Unknown | Unknown | Jonathon Cook | 2022-05-18 08:54 AM MST | 100.0% | 0.0% | 101 | 66 | 0 | 0 | 167
Montrose PD | Unknown | Unknown | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 5
Gunnison HWY 50 - Stryer | Unknown | Unknown | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 33
State of Colorado Offices 2021 | Unknown | Unknown | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 54
Norwood Gardens | Unknown | Unknown | Jonathon Cook | 2021-12-17 03:13 AM MST | 100.0% | 0.0% | 32 | 0 | 0 | 0 | 32
Olathe | Unknown | Unknown | Jonathon Cook | 2022-07-07 06:33 AM MST | 100.0% | 0.0% | 26 | 22 | 0 | 0 | 48
Meadowlark Lane Drop | Unknown | Unknown | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 3
Montrose Woods Crossing Feed | Unknown | Unknown | admin3@pothosgeospatial.com | 2024-03-05 09:48 AM MST | 100.0% | 100.0% | 25 | 7 | 0 | 0 | 35
Montrose Vernal Rd Feed | Unknown | Unknown | riley.mcneil@clearnetworx.com | 2023-02-16 05:37 AM MST | 98.4% | 0.0% | 0 | 0 | 0 | 0 | 61
Grand Valley Poles in Orchard Mesa | Unknown | Unknown | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 617
Montrose La Salle Rd | Unknown | Unknown | Jonathon Cook | 2022-07-08 02:55 AM MST | 100.0% | 0.0% | 17 | 4 | 0 | 0 | 21
Palisade Town Build | Unknown | Unknown | riley.mcneil@clearnetworx.com | 2024-01-13 04:54 AM MST | 100.0% | 61.2% | 288 | 7 | 0 | 0 | 298
Fruita Town Build | Unknown | Unknown | riley.mcneil@clearnetworx.com | 2024-10-08 01:06 AM MST | 96.4% | 89.5% | 560 | 72 | 0 | 0 | 690
60571 Maple Grove Rd Build | Unknown | Unknown | riley.mcneil@clearnetworx.com | 2023-02-09 06:35 AM MST | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 26
Forest Products | Unknown | Unknown | Jonathon Cook | 2023-04-24 03:58 AM MST | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 62
Delta Aspen Way | Unknown | Unknown | Jonathon Cook | 2023-04-24 03:53 AM MST | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 6
Montrose Townsend Ave | Unknown | Unknown | riley.mcneil@clearnetworx.com | 2023-02-15 06:01 AM MST | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 41
CORTEZ | Unknown | Unknown | riley.mcneil@clearnetworx.com | 2023-03-15 11:50 AM MST | 99.2% | 0.0% | 0 | 0 | 0 | 0 | 120
793 orchard | Unknown | Unknown | Jonathon Cook | 2023-06-07 01:24 AM MST | 100.0% | 0.0% | 1 | 0 | 0 | 0 | 3
1008 oak grove | Unknown | Unknown | riley.mcneil@clearnetworx.com | 2023-02-09 06:38 AM MST | 100.0% | 0.0% | 1 | 0 | 0 | 0 | 2
delta 1600 | Unknown | Unknown | Jonathon Cook | 2023-04-21 06:02 AM MST | 100.0% | 0.0% | 77 | 3 | 0 | 0 | 81
Delta Pole as Built | Unknown | Unknown | riley.mcneil@clearnetworx.com | 2023-03-13 02:18 AM MST | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 130
Delta Technical College | Unknown | Unknown | riley.mcneil@clearnetworx.com | 2023-03-23 11:01 AM MST | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 63
CORTEZS1 | Unknown | Unknown | Jonathon Cook | 2023-10-16 08:34 AM MST | 100.0% | 1.0% | 1 | 1 | 0 | 0 | 104
DOLORESSTATEBANK | Unknown | Unknown | riley.mcneil@clearnetworx.com | 2023-06-20 02:44 AM MST | 100.0% | 100.0% | 27 | 1 | 0 | 0 | 30
fruita50run | Unknown | Unknown | riley.mcneil@clearnetworx.com | 2023-07-07 04:33 AM MST | 100.0% | 100.0% | 7 | 8 | 0 | 0 | 15
PRACTICE | Unknown | Unknown | gavin.walsh@deeplydigital.com | 2023-08-16 04:17 AM MST | 100.0% | 0.0% | 3 | 0 | 0 | 0 | 63
gavinpractice | Unknown | Unknown | gavin.walsh@deeplydigital.com | 2023-09-14 03:37 PM MST | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 63
Dolores State Bank | Unknown | Unknown | Jonathon Cook | 2023-09-06 06:39 AM MST | 100.0% | 100.0% | 13 | 0 | 0 | 0 | 13
CORTEZS-3 | Unknown | Unknown | michael.espinal@deeplydigital.com | 2024-05-15 06:47 AM MST | 100.0% | 97.4% | 73 | 40 | 8 | 0 | 121
GJ0Z14-3P | Unknown | Unknown | Jonathon Cook | 2023-09-11 12:44 AM MST | 100.0% | 0.0% | 2 | 0 | 0 | 0 | 66
dolores PRACTICE | Unknown | Unknown | gavin.walsh@deeplydigital.com | 2023-10-03 05:05 AM MST | 99.6% | 0.4% | 0 | 0 | 0 | 0 | 237
dolores practice | Unknown | Unknown | gavin.walsh@deeplydigital.com | 2023-10-03 05:05 AM MST | 99.6% | 0.0% | 0 | 0 | 0 | 0 | 237
cr12ridgway | Unknown | Unknown | Jonathon Cook | 2023-12-15 04:41 AM MST | 88.9% | 0.0% | 15 | 1 | 0 | 0 | 18
palisade-bower | Unknown | Unknown | riley.mcneil@clearnetworx.com | 2023-11-29 12:24 AM MST | 100.0% | 0.0% | 2 | 0 | 0 | 0 | 2
Gunnison Saw Tooth | Unknown | Unknown | Jonathon Cook | 2023-12-13 04:32 AM MST | 100.0% | 100.0% | 4 | 0 | 0 | 0 | 4
gunnisontownbuild | Unknown | Unknown | riley.mcneil@clearnetworx.com | 2023-12-07 07:18 AM MST | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 26
montrose-olathe - From Deeply Digital_ | Unknown | Unknown | Jonathon Cook | 2024-02-22 07:23 AM MST | 97.2% | 95.0% | 129 | 12 | 0 | 0 | 145
ArchuletaCountyCPF_Master | Unknown | Unknown | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 572
Katapult_Training | Unknown | Unknown | admin3@pothosgeospatial.com | 2024-04-19 02:32 AM MST | 90.0% | 100.0% | 0 | 1 | 1 | 0 | 10
Fruita Palisade Middle Mile - Fruita to I-70 and 24 Rd | Unknown | Unknown | riley.mcneil@clearnetworx.com | 2024-08-05 04:37 PM MST | 100.0% | 1.5% | 6 | 0 | 0 | 0 | 270
Fruita Palisade Middle Mile - 29 Rd and Patterson to Palisade | Unknown | Unknown | riley.mcneil@clearnetworx.com | 2023-05-18 02:43 AM MST | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 329
API Layers Testing | Unknown | Unknown | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 2
61706 Monroe road | Unknown | Unknown | zach.marin@deeplydigital.com | 2024-05-13 07:33 AM MST | 66.7% | 0.0% | 0 | 0 | 0 | 0 | 6
Fruit_Park | Unknown | Unknown | admin3@pothosgeospatial.com | 2024-07-16 02:18 AM MST | 95.2% | 0.0% | 0 | 0 | 0 | 0 | 21
691 Spring Creek Rd Montrose | Unknown | Unknown | mady@clearnetworx.com | 2024-08-28 02:35 PM MST | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 4
Montrose Infill North | Unknown | Unknown | michael.espinal@deeplydigital.com | 2024-08-15 01:29 AM MST | 98.7% | 0.4% | 0 | 1 | 0 | 0 | 232
Hwy160_MM_Laterals | Unknown | Unknown | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 58
DurangoE3_Extras | Unknown | Unknown | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 6
HWE-2D-EXT-D - From Amplex Electric, Inc. | Unknown | Unknown | Unknown | Unknown | 100.0% | 0.0% | 0 | 0 | 0 | 0 | 1
GJ_D3-1 | Xcel | Delivered | riley.mcneil@clearnetworx.com | 2024-12-30 02:49 AM MST | 100.0% | 100.0% | 19 | 36 | 0 | 0 | 55
GJ_D3-4 | Xcel | Delivered | jordan.demers@deeplydigital.com | 2024-08-08 09:39 AM MST | 100.0% | 100.0% | 38 | 53 | 13 | 4 | 108
GJ_D3-EXTRA | Xcel | Hold | riley.mcneil@clearnetworx.com | 2024-10-01 10:08 AM MST | 98.8% | 16.0% | 7 | 0 | 0 | 3 | 82
GJ_D5-4 | Xcel Energy | Approved for Construction | riley.mcneil@clearnetworx.com | 2024-10-03 04:48 AM MST | 100.0% | 100.0% | 21 | 19 | 14 | 1 | 55
GJ_D3-5 | Xcel Energy | Approved for Construction | riley.mcneil@clearnetworx.com | 2024-09-24 03:17 AM MST | 100.0% | 100.0% | 28 | 2 | 3 | 0 | 33
GJ_D4-3 | Xcel Energy | Delivered | riley.mcneil@clearnetworx.com | 2024-08-09 03:10 AM MST | 100.0% | 100.0% | 25 | 12 | 19 | 3 | 59
GJ_D4-1 | Xcel Energy | Delivered | jordan.demers@deeplydigital.com | 2024-08-13 08:51 AM MST | 98.9% | 100.0% | 57 | 15 | 14 | 1 | 87
GJ_D4-2 | Xcel Energy | Delivered | riley.mcneil@clearnetworx.com | 2024-09-27 04:35 AM MST | 99.0% | 100.0% | 38 | 34 | 23 | 7 | 102
GJ_D5-1 | Xcel Energy | Delivered | riley.mcneil@clearnetworx.com | 2024-10-17 01:41 AM MST | 100.0% | 100.0% | 9 | 0 | 1 | 0 | 10
GJ_D5-2 | Xcel Energy | Delivered | riley.mcneil@clearnetworx.com | 2024-10-22 01:23 AM MST | 99.0% | 100.0% | 44 | 40 | 17 | 0 | 101
GJ_D5-3 | Xcel Energy | Delivered | riley.mcneil@clearnetworx.com | 2024-10-17 11:58 PM MST | 100.0% | 100.0% | 69 | 26 | 16 | 0 | 112
GJ_D5-5 | Xcel Energy | Delivered | riley.mcneil@clearnetworx.com | 2024-10-09 11:45 PM MST | 100.0% | 100.0% | 27 | 29 | 13 | 0 | 69
GJ_D3-2-3 | Xcel Energy | Delivered | michael.espinal@deeplydigital.com | 2024-08-12 01:12 AM MST | 100.0% | 100.0% | 2 | 6 | 0 | 0 | 8
GJ_D2-4-5 | Xcel Energy | Hold | gavin.walsh@deeplydigital.com | 2024-08-01 08:19 AM MST | 96.1% | 0.0% | 0 | 0 | 0 | 0 | 51
GJ_D5Extras | Xcel Energy | Junk | riley.mcneil@clearnetworx.com | 2024-10-12 04:52 AM MST | 100.0% | 6.1% | 10 | 3 | 1 | 1 | 45
GJ_C2 | Xcel Energy | Pending Photo Annotation | riley.mcneil@clearnetworx.com | 2024-12-31 11:52 PM MST | 86.4% | 0.0% | 0 | 0 | 0 | 0 | 125
Parachute1 | Xcel energy | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 102
Parachute2 | Xcel energy | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 28
Parachute3 | Xcel energy | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 59
Parachute4 | Xcel energy | Pending Field Collection | Unknown | Unknown | 0.0% | 0.0% | 0 | 0 | 0 | 0 | 76
GJ_D9-1 | Xcel energy | Pending Photo Annotation | Unknown | Unknown | 75.8% | 0.0% | 0 | 0 | 0 | 0 | 157