## Aerial Status Report
Aerial Status Report
1/2/2025 1:42 PM
Job Name | Conversation | Project | Utility | Job Status | Assigned OSP | Last Edit | Field % | Trace % | No MR | Comm MR | Electric MR | PCO Required | Pole Count
FRM_5-1 | 1778525, 1778509, 1778478, 1778477, 1778474, 1778111 | FRM_5 | FEUS | Delivered | Hector | 2024-12-05 08:45 AM MST | 99.4% | 100.0% | 109 | 47 | 8 | 3 | 168
LP_CPF_Vallecito_S5 | 12345676 | LP_CPF | LPEA | Sent to PE | Anthony | 2024-12-30 03:11 AM MST | 100.0% | 100.0% | 72 | 0 | 0 | 0 | 72
GJD1-3_Extras | Riley to Populate |  | Xcel Energy | Approved for Construction | Riley | 2024-05-02 12:24 AM MST | 100.0% | 100.0% | 1 | 0 | 0 | 0 | 1
GJ_A5_1.1 | 1782232 | GJ_A5 | Xcel Energy | Pending Photo Annotation | Michael | 2025-01-02 06:40 AM MST | 95.9% | 35.6% | 11 | 5 | 0 | 0 | 49